## Slide 1
CHAPTER 3
Agile Software
Development

## Slide 2
Topics Covered
Chapter 3 — Agile Software Development • Overview
1
3.1 Agile methods
3.2 Plan-driven and agile development
3.3 Extreme programming
3.4 Agile project management
3.5 Scaling agile methods

## Slide 3
3.1
Agile Methods
Why software teams moved away from heavyweight, plan-driven processes
2

## Slide 4
Why Rapid Development Matters
Chapter 3 — Agile Software Development • 3.1 Agile Methods
3
Businesses operate in a global, rapidly changing environment
Software must respond to new opportunities, markets, and competitive pressure
It is often practically impossible to derive a complete, stable set of requirements up front
The “real” requirements frequently only become clear after users work with a delivered system
Conventional waterfall / specification-based processes struggle to keep pace — rework is constant as requirements change
Notes: Waterfall is the classic plan-driven software process model — the one Ch3 contrasts agile against. From your Ch2 lecture, the key points:
Structure: A strict sequence of distinct phases, each completed before the next begins:
Requirements definition
System and software design
Implementation and unit testing
Integration and system testing
Operation and maintenance
Core idea: Each phase produces a formal document/output that becomes the input to the next phase. There's no going back — the model assumes you can get each phase "right" before moving on.
Main drawback (per Ch2): Inflexibility. Once a phase is done, revisiting it is difficult and costly. This makes waterfall a poor fit when requirements are likely to change during development — which is exactly the problem agile methods were designed to solve.
When it still makes sense:
Requirements are well-understood and unlikely to shift
The system is large, safety-critical, or heavily regulated (aerospace, government) — where a complete upfront specification is actually necessary
Work is distributed across multiple organizations/sites, where formal documents are needed to coordinate between teams
The through-line to Ch3: waterfall is the plan-driven end of the spectrum Sommerville uses throughout — agile isn't "waterfall's replacement," it's the other end of a continuum, and the real skill (as your slides frame it) is judging which factors push a project toward one end or the other, or toward a hybrid.

## Slide 5
A Brief History
Chapter 3 — Agile Software Development • 3.1 Agile Methods
4
1980s
IBM introduces incremental development (Mills et al.)
1980s
Fourth-generation languages support rapid delivery (Martin)
Late 1990s
DSDM, Scrum, and Extreme Programming emerge (Stapleton; Schwaber & Beedle; Beck)
Since
Shared principles are captured in the Agile Manifesto
Notes: These are the three landmark agile methods that crystallized the movement in the late 1990s — the moment Chapter 3 marks as when "the notion really took off."
DSDM (Dynamic Systems Development Method) — introduced by Stapleton in 1997. One of the earliest formalized agile frameworks, built around iterative, incremental development with strong emphasis on active user involvement and frequent delivery. It's less well-known today than Scrum or XP but was historically significant as one of the first attempts to codify rapid application development into a repeatable method.
Scrum — introduced by Schwaber and Beedle in 2001 (though the ideas trace earlier). Scrum is a project management framework, not a set of engineering practices — it doesn't tell you how to code, only how to organize the work. Its core structure: fixed-length sprints (2-4 weeks), a prioritized product backlog, daily stand-up meetings, and a Scrum Master who shields the team from external distractions. This is the method covered in Ch3.4 of your slides.
Extreme Programming (XP) — introduced by Kent Beck, 1999/2000. Unlike Scrum, XP is deeply prescriptive about engineering practice: test-first development, pair programming, continuous integration, refactoring, collective code ownership. Beck's idea was to take practices already known to be good (like iterative development and code review) and push them to "extreme" levels — hence the name. This is Ch3.3 in your slides.
Why "emerge" together matters: these three arrived within a few years of each other, independently, from different practitioners — and that convergence is why the Agile Manifesto got written in 2001. The manifesto wasn't the starting point; it was leaders from DSDM, Scrum, XP, Crystal, and others recognizing they'd separately arrived at overlapping principles and deciding to name what they shared. That's the actual sequence: independent practice → convergence → manifesto, not the reverse.
"The agile method" is a family of related approaches (Scrum, XP, DSDM, Crystal, and others) that share a common philosophy, formalized in the 2001 Agile Manifesto. If you're looking for a single definition that covers what they all have in common:
Agile methods are incremental development approaches where software is built and delivered in small, frequent releases (often every 2-4 weeks) rather than as one large delivery at the end of a long process. The defining characteristics:
Specification, design, and implementation happen together, not as separate sequential phases — there's no complete upfront spec
The customer is closely involved throughout, evaluating each increment and reprioritizing what comes next
Documentation is minimized in favor of working software and informal communication
Change is expected and embraced, not treated as a disruption to a fixed plan
This sits in direct contrast to plan-driven (waterfall) development, where requirements, design, implementation, and testing are distinct sequential stages, each producing formal documents before the next begins.
The philosophy is captured in the Agile Manifesto's four value statements: individuals and interactions over processes and tools, working software over comprehensive documentation, customer collaboration over contract negotiation, and responding to change over following a plan.
If you meant a specific one — Scrum (project management framework) or XP (engineering practices like pair programming and test-first development) are the two most commonly taught — let me know and I can go deeper on either.

## Slide 6
The Agile Manifesto
Chapter 3 — Agile Software Development • 3.1 Agile Methods
5
Individuals and interactions over processes and tools
Working software over comprehensive documentation
Customer collaboration over contract negotiation
Responding to change over following a plan
“While there is value in the items on the right, we value the items on the left more.”

## Slide 7
Principles of Agile Methods
Chapter 3 — Agile Software Development • 3.1 Agile Methods
6
1
Customer involvement
Customers are closely involved throughout — prioritizing requirements and evaluating each iteration.
2
Incremental delivery
Software is developed in increments, with the customer specifying what each increment includes.
3
People, not process
Recognize and exploit the team's skills; let the team develop its own ways of working.
4
Embrace change
Expect requirements to change, and design the system to accommodate that.
5
Maintain simplicity
Focus on simplicity in the software and the process; actively eliminate complexity.

## Slide 8
Where Agile Methods Succeed — and Where They Struggle
Chapter 3 — Agile Software Development • 3.1 Agile Methods
7
Strong fit:
  Product development — a small/medium-sized product built for sale
  Custom development — a committed customer, few external regulatory constraints
Weaker fit:
  Safety-critical or heavily regulated systems that need complete up-front analysis
  These require significant modification of agile practice — a preview of Chapters 12 and 13

## Slide 9
Agile Principles Are Hard to Realize
Chapter 3 — Agile Software Development • 3.1 Agile Methods
8
The Challenges
The Cost of Skipping Them
Success depends on a willing, available customer who can represent all stakeholders
Not every team member has the personality suited to intense, continuous involvement
Prioritizing changes is difficult when many stakeholders disagree
Maintaining simplicity takes extra work — easy to skip under deadline pressure
Large organizations often have years of process culture that resist informal, team-defined ways of working
None of this is automatic — discipline is still required

## Slide 10
Agile Methods and Software Maintenance
Chapter 3 — Agile Software Development • 3.1 Agile Methods
9
Agile advocates argue: well-structured, readable code matters more than formal documentation that quickly goes stale
Counter-argument: the requirements document is often the key artifact for understanding system intent during maintenance
Agile methods that collect requirements informally and incrementally may leave no coherent requirements record
Risk: this can make later maintenance more difficult and costly — especially if the original team disperses and its implicit knowledge is lost

## Slide 11
3.2
Plan-Driven and Agile Development
Two different ways of organizing the same underlying activities
10

## Slide 12
Two Approaches to Specification
Chapter 3 — Agile Software Development • 3.2 Plan-Driven vs. Agile
11
Plan-Based Development
Requirements
Engineering
Requirements
Specification
Design and
Implementation
Agile Development
Requirements
Engineering
Design and
Implementation
Requirements change requests flow continuously between the two activities
Plan-driven: iteration happens within a stage; formal documents connect the stages. Agile: the requirements and the design evolve together.

## Slide 13
Choosing an Approach (1 of 2)
Chapter 3 — Agile Software Development • 3.2 Plan-Driven vs. Agile
12
1
Detailed spec needed?
If a very detailed specification and design must exist before implementation, lean plan-driven.
2
Rapid feedback realistic?
If incremental delivery with fast customer feedback is realistic, agile fits well.
3
Team size & location
Agile works best for small, co-located teams who communicate informally.
4
System type
Systems needing heavy up-front analysis (e.g., real-time timing constraints) often need plan-driven design.
5
Expected lifetime
Long-lived systems may need more documentation to communicate intent to future maintainers.

## Slide 14
Choosing an Approach (2 of 2)
Chapter 3 — Agile Software Development • 3.2 Plan-Driven vs. Agile
13
1
Tooling
Good visualization and analysis tools support agile; without them, more design documentation is needed.
2
Team organization
Distributed or outsourced teams often need documentation to coordinate across sites.
3
Organizational culture
Engineering cultures built around plan-based work usually expect extensive documentation.
4
Team skill level
Agile methods generally assume a highly skilled team; lower-skill teams may need more up-front design.
5
External regulation
Regulated systems (e.g., aviation software) typically require detailed documentation as part of approval.

## Slide 15
3.3
Extreme Programming (XP)
The best-known agile method — recognized good practice, pushed to the extreme
14

## Slide 16
The XP Release Cycle
Chapter 3 — Agile Software Development • 3.3 Extreme Programming
15
Coined by Kent Beck — pushes recognized good practice (like iterative development) to ‘extreme’ levels
Requirements are expressed as user stories, broken into tasks
Programmers work in pairs and write tests before code
All tests must pass before new code is integrated
Plan
Release
Select
Stories
Break Into
Tasks
Develop &
Integrate
Release
Software
Evaluate
System

## Slide 17
XP Practices (1 of 2)
Chapter 3 — Agile Software Development • 3.3 Extreme Programming
16
1
Incremental planning
Requirements live on story cards; the team breaks stories into tasks and prioritizes by value.
2
Small releases
The minimal useful set of functionality ships first; releases follow frequently.
3
Simple design
Enough design to meet the current requirements — and no more.
4
Test-first development
An automated test is written for new functionality before that functionality is implemented.
5
Refactoring
Developers continuously improve code structure as soon as a possible improvement is found.

## Slide 18
XP Practices (2 of 2)
Chapter 3 — Agile Software Development • 3.3 Extreme Programming
17
1
Pair programming
Developers work in pairs, checking each other's work as they go.
2
Collective ownership
Pairs work across the whole system — anyone can change any part of the code.
3
Continuous integration
As soon as a task is done, it's integrated; all unit tests must pass afterward.
4
Sustainable pace
Excessive overtime is discouraged — it tends to lower code quality and productivity.
5
On-site customer
A customer representative is embedded full-time with the team, defining acceptance tests.

## Slide 19
User Stories & Task Cards
Chapter 3 — Agile Software Development • 3.3 Extreme Programming
18
Story Card — Prescribing Medication
A doctor selects a patient's medication as ‘current’, ‘new’, or from the ‘formulary’.
For each path, she chooses the drug and enters a dose.
The system always checks the dose against a safe range before allowing confirmation.
The confirmed prescription is recorded to an audit database.
Task Cards Derived From the Story
Task 1
Change dose of a prescribed drug
Task 2
Formulary selection
Task 3
Dose checking — a safety precaution confirming the dose is neither dangerously low nor high
Notes: Here's the full picture, with each task traced back to its exact origin in the story:
The three branches in the story
The doctor can prescribe medication three different ways:
Current medication — the drug is already known (patient's already on it); she just checks/adjusts the dose
New medication — she types in a drug she hasn't prescribed before, picks from suggestions
Formulary — she searches an approved reference list to find a drug
Then, regardless of which path she took, two things always happen afterward: the dose gets checked against a safe range, and once confirmed, it's logged.
Now the three tasks, mapped to their source:
Task 1 — Change dose of a prescribed drug → Comes from the "current medication" branch. The drug itself isn't in question — the only work here is: show the existing dose, let her edit it, accept the new value. Narrow, self-contained piece of logic.
Task 2 — Formulary selection → Comes from the "formulary" branch. This is a different kind of work entirely — searching a reference list, letting her pick a result. Nothing to do with adjusting an existing dose.
Task 3 — Dose checking → This one's different from the other two. It doesn't come from one branch — it comes from the part of the story that says the dose is always validated, no matter which path got you there. Since all three branches eventually produce "a dose was entered," dose-checking gets pulled out as its own reusable task rather than being built three separate times inside each branch.
One honest gap to flag: the story actually has a fourth branch — "new medication" — where she manually searches by typing drug-name letters. That branch would logically need its own task too (something like "New medication search"), the same way formulary search got one. The original example only shows three task cards, so either that task exists but wasn't pictured, or the team judged it similar enough to Task 2's search mechanism to fold in. Worth noting as a loose thread rather than something to paper over.
The pattern to take away: tasks map to branches of behavior in the story, except where behavior is shared across branches — that shared behavior becomes its own task instead of being duplicated.

## Slide 20
Testing in XP
Chapter 3 — Agile Software Development • 3.3 Extreme Programming
19
Test-first development — write the test before the code it tests
Tests are developed incrementally from user story scenarios
The customer helps define acceptance tests for each story
Automated test frameworks (e.g., PyTest) make it cheap to run the full suite constantly
Caveat:
  Programmers may write incomplete tests under time pressure
  Some behavior (like UI display logic) is hard to test incrementally
  A large, frequently-run test suite can still leave real coverage gaps

## Slide 21
Pair Programming
Chapter 3 — Agile Software Development • 3.3 Extreme Programming
20
Why Teams Use It
What the Evidence Shows
Supports collective ownership — no single point of blame for the code
Acts as a cheap, informal, continuous code review
Makes refactoring easier — the whole pair benefits immediately
Some studies (student teams) found productivity comparable to two people working alone
Studies with experienced programmers found a real productivity cost
Either way, shared knowledge reduces the risk when a team member leaves

## Slide 22
3.4
Agile Project Management
Scrum — a management framework for iterative development
21

## Slide 23
The Scrum Process
Chapter 3 — Agile Software Development • 3.4 Agile Project Management
22
Outline Planning &
Architectural Design
Assess
Select
Develop
Review
Sprint Cycle
(2–4 weeks)
Project
Closure
Each sprint delivers a working increment of the system to stakeholders.

## Slide 24
Anatomy of a Sprint
Chapter 3 — Agile Software Development • 3.4 Agile Project Management
23
Fixed length — typically 2 to 4 weeks
Starts from the product backlog, reviewed and prioritized with the customer
The whole team selects the features to build during the sprint
Short daily ‘stand-up’ meetings track progress and surface problems
The Scrum Master shields the team from external distractions — not a traditional ‘project manager’
The sprint ends with a review and demo to stakeholders

## Slide 25
Why Scrum Works (Rising & Janoff)
Chapter 3 — Agile Software Development • 3.4 Agile Project Management
24
Breaks the product into manageable, understandable chunks
Unstable requirements don't have to block progress
Whole-team visibility improves communication
Customers see on-time delivery and give real, working feedback
Builds trust between customers and developers

## Slide 26
3.5
Scaling Agile Methods
Agile was built for small teams — large systems need adaptation
25

## Slide 27
Why Large Systems Are Different
Chapter 3 — Agile Software Development • 3.5 Scaling Agile Methods
26
1
Distributed teams
Large systems are collections of separate systems, often built by teams in different places and time zones.
2
‘Brownfield’ systems
Large systems must interact with existing systems — flexibility is constrained by what's already there.
3
Integration effort
A significant share of the work is system configuration, not new code.
4
External constraints
Rules, regulations, and required documentation often shape the process.
5
Long timelines
Long procurement and development periods make it hard to keep a coherent team together.
6
Diverse stakeholders
It's often impossible to involve every stakeholder group directly.

## Slide 28
Scaling Up vs. Scaling Out
Chapter 3 — Agile Software Development • 3.5 Scaling Agile Methods
27
Two Perspectives
Critical Adaptations
Scaling up:
  Using agile methods for genuinely large systems that no small team could build alone
Scaling out:
  Introducing agile practice across a large organization with an established plan-driven culture
More up-front design and architecture documentation
Deliberate cross-team communication channels (video, wikis, chat)
Frequent builds and releases, even where full continuous integration isn't realistic

## Slide 29
Barriers to Adoption in Large Organizations
Chapter 3 — Agile Software Development • 3.5 Scaling Agile Methods
28
Managers unfamiliar with agile may be reluctant to accept the risk on their projects
Existing quality standards and mandated tools often conflict with agile practice
Skill-level variance across large teams undermines agile's assumption of a highly skilled team
Cultural resistance in organizations built around long-standing, plan-driven processes

## Slide 30
Key Points
Agile methods are incremental, customer-involved, and low-overhead by design
The choice between agile and plan-driven depends on system type, team, and organizational culture — not ideology
Extreme Programming combines frequent releases, continuous improvement, customer participation, and test-first development
Scrum is a project-management framework built around fixed-length sprints and a prioritized backlog
Scaling agile to large systems is genuinely difficult — some up-front design and documentation becomes necessary
29

## Slide 31
Discussion
Agile & Our Structured Prompt Library
This chapter maps to the Week 3 entry in our prompt library: scoping a project and choosing a process model
Sommerville: “There are no right or wrong software processes.” Does the same apply to prompting techniques?
Is ‘vibe coding’ agile without discipline — or is it no process at all?
30